## Phase 3
Track Muse – Phase 3 Estimate |  |  | 3
· home page |  |  | 1
o add rotator at seven seconds 1h |  |  | 1
o remodel top of screen 3h |  |  | 6
· pictures page |  |  | 1
o assuming the rotating background pictures established in the home screen is the same set of pictures that will display on the pictures page. Please correct if wrong. |  |  | 1
§ add one to many support for background picture in schema 0h |  |  | 1
§ add ability to maintain list of background pictures (including add) 0h |  |  | 5
§ add rotator at seven seconds 0h |  |  | 4
o add click on stock photo edit page 1h |  |  | 4
§ add label to schema |  |  | 27
o add click on project photo links to project page 1h |  |  | 575
o change hover text 1h |  |  | 21.2963
§ if stock then label else project name else filename
· Manage background pictures screen (new)
o Create 1h |  |  | 28 | total hours for ph 3
o Add one to many support for background picture in schema 1h |  |  | 596.2963 | total $ for ph3
o Add ability to maintain list of background pictures (including add) 2h |  |  | 59.6296 | preferred customer discount
· Forum |  |  | 536.6667 | total after discount
o Add forum to the project |  |  | 15.8633 | convenience fee
§ Create forum schema 1h |  |  | 552.53 | total with convenience fee
§ Add one to many links to images for each forum post |  | 675 |  | lost convenience fees
§ Add the ability for admins to moderate the forum 2h |  |  | 552.53 | total with convenience fee recovery
o Add forum screen 6h
· Profile screen
o Add manage background pictures button
o Change name and links to Your Garage
o design project boxes 2h | 2
o add profile image to schema and screen 2h | 2
o add ability to change profile image 1h | 1
o add background image to schema and screen and add ability to change it 1h | 1
· Project screen
o design project screen 2h | 2
o add project description field to schema and screen 1h | 1
o modify code to set fields as required and provide user feedback when requirement is met 1h | 1
§ fields
· project name
· year
· model
· make
· trim
· description
o change schema to 1h | 1
§ allow many car photos per project
§ add description field for each car photo
§ add label field for each car
§ add cover photo flag
o add scrolling list of car photos for the project 4h | 4
o add popup when pic is click in scroll (edit or read only depending) 2h | 2
o create schema to support forum 1h | 1
o update screen to support forum 2h | 2
o add parts to schema and link to project 1h | 1
o add parts list maintenance, borrowing heavily from project pictures 3h | 3
§ parts fields (all required)
· Name
· Description
· price paid
· link back to the vendor’s page
o Add forum to the project
§ Create forum schema 1h | 1
§ Add one to many links to images for each forum post 1h | 1
§ Add the ability for admins to moderate the forum 2h | 2
· Manage users screen
o No changes
· Manage stock photos screen
o No changes
· Manage news screen
o No changes
Total: 46 hrs

## Phase 4.0
Phase 4.0
Task | Estimate
launch site | 1
Change “Forum” to “Comments | 2
ensure no impact to main forum
Reorder photos, parts and newsfeed | 1
Omit parts section if blank on photo landing | 1
Add save button to foreground image | 1
offer list of projects and prompt to select | 2
dynamic project creation | 4
add part if project exists | 0
temporary cache of part until project creation is complete | 1
add share button to expose image link | 1
create parts landing page | 3
include strip of parts, no images | 2
parts from the strip reload the landing page | 1
make trim and year fields optional | 1
create full screen photo screen | 3
click on photo gives all photos option | 3
hover icon indicator indicates the option | 2
Total estimate | 29
$/hr | 21
$ Project cost | 609
Preferred ustomer discount | 60.9
Cost - discount | 548.1
Convenience Fee Charge-back | 16.1949
Total | 564.2949